## Initail testing
Test case
PROJECT NAME : 112510- Automated Mail for gold loan leads
Software Request ID : |  |  | 112510 |  | Project End Date
Created by: |  |  | Naina Nasrin |  | Delay
Created Date: |  |  | 2022-07-13 |  | Testing Date | 2022-07-13
Reviewed By |  |  | Joby Jose |  | Time
Version |  |  |  |  | UAT Retesting
Test Engineer: |  |  | Naina Nasrin
Date | TEST CASE ID | TEST CASE NAME | TEST CASE OBJECTIVE | TEST DATA/INPUT | EXPECTED RESULT | ACTUAL RESULT | ESTIMATED TIME | ACTUAL TIME | SEVERITY | TEST STAGE | TEST STATUS | REMARKS
2022-07-13 | TC-01 | Gold loan lead-CRM | Check whether the gold loan lead in CRM automated mail send to HO sales team is available or not |  | The gold loan lead in CRM automated should be mail to HO sales team | The gold loan lead in CRM automated mail send to HO sales team | 0.5 | 0.5 | High | Initial testing | Passed | Passed
2022-07-13 | TC-02 | Gold loan lead-CRC | Check whether the gold loan lead in CRC automated mail send to HO sales team is available or not |  | The gold loan lead in CRC automated should be mail to HO sales team | The gold loan lead in CRC automated mail send to HO sales team | 0.5 | 0.5 | High | Initial testing | Passed | Passed
2022-07-13 | TC-03 | Daily gold load leads | Check whether the daily gold loan leads of online gold loan, gold loan, door step gold loan, take over goald loan details are available to user |  | The daily gold loan leads of online gold loan, gold loan, door step gold loan, take over goald loan details are available to user | The daily gold loan leads of online gold loan, gold loan, door step gold loan, take over goald loan details are available to user | 0.5 | 0.5 | High | Initial testing | Passed | Passed
2022-07-13 | TC-04 | Dash board details | Check whether the product, MTD, yesterday and grand total details are displayed correctly in dashboard |  | The product, MTD, yesterday and grand total details are displayed correctly in dashboard | The product, MTD, yesterday and grand total details are displayed correctly in dashboard | 0.5 | 0.5 | High | Initial testing | Passed | Passed
2022-07-13 | TC-05 | Attachment | Check whether the daily gold lead dashboard data attached with automated mail |  | The daily gold lead dashboard data should be attached with automated mail | The daily gold lead dashboard data attached with automated mail | 0.5 | 0.5 | High | Initial testing | Passed | Passed